## communication plan
# | Stakeholder | Communication Type | Frequency | Mode | Owner
1 | CDO (Sponsor) | Project Status Update | Weekly | Email + Dashboard | Project Manager
2 | Product Owner | Backlog Grooming | Bi-weekly | Meeting (Scrum) | BA / Scrum Master
3 | Project Manager | Progress & Risk Updates | Daily/Weekly | Stand-up + Reports | BA Team
4 | Development Team | Requirements Clarification | Daily | Stand-ups / Slack | BA
5 | QA Team | Test Case Review | Sprint-wise | Meetings | BA / QA Lead
6 | Head of Retail Lending | Business Updates | Monthly | Presentation | PM / BA
7 | Loan Officers | Training & Feedback | Pre & Post Release | Workshops | BA / Training Team
8 | IT Security Team | Compliance Review | Milestone-based | Meetings | PM / Security Lead
9 | Legal & Compliance | Regulatory Updates | Milestone-based | Documentation Review | BA
10 | End Customers | Feedback Collection | Post-launch | Surveys / App Feedback | Product Team
11 | Vendor (Core Banking) | Integration Updates | Weekly | Technical Calls | IT Team