## RACI
Activity / Deliverable | CDO | PO | PM | BA | Dev | QA | Business | IT Sec | Vendor
Business Requirements | A | R | C | R | C | C | C | C | C
Solution Design | C | A | C | R | R | C | C | C | R
Development | C | C | A | C | R | C | I | C | R
Testing (SIT/UAT) | I | C | A | C | C | R | R | C | C
Deployment | A | C | R | C | R | C | I | C | R
Compliance Approval | I | I | C | C | I | I | I | R | C
Training & Rollout | C | A | R | R | I | C | R | I | I
R (Responsible) → Does the work A (Accountable) → Final decision maker C (Consulted) → Provides input I (Informed) → Kept updated

## Communication Plan
# | Stakeholder | Communication Type | Frequency | Mode | Owner
1 | CDO (Sponsor) | Project Status Update | Weekly | Email + Dashboard | Project Manager
2 | Product Owner | Backlog Grooming | Bi-weekly | Meeting (Scrum) | BA / Scrum Master
3 | Project Manager | Progress & Risk Updates | Daily/Weekly | Stand-up + Reports | BA Team
4 | Development Team | Requirements Clarification | Daily | Stand-ups / Slack | BA
5 | QA Team | Test Case Review | Sprint-wise | Meetings | BA / QA Lead
6 | Head of Retail Lending | Business Updates | Monthly | Presentation | PM / BA
7 | Loan Officers | Training & Feedback | Pre & Post Release | Workshops | BA / Training Team
8 | IT Security Team | Compliance Review | Milestone-based | Meetings | PM / Security Lead
9 | Legal & Compliance | Regulatory Updates | Milestone-based | Documentation Review | BA
10 | End Customers | Feedback Collection | Post-launch | Surveys / App Feedback | Product Team
11 | Vendor (Core Banking) | Integration Updates | Weekly | Technical Calls | IT Team